## Implementation Plan
Recommended Implementation Time
Item # | Who's Responsible | Topic | Task (What needs done) | Communicate? | Start Date | Implement Date | Nov. | Dec. | Jan. | Feb. | March | April | May | June | July | August | Sept. | Oct. | Update on implementation 30 Day | Update on implementation 60 Day | Update on implementation 90 Day | Update on implementation 6 Months | Update on implementation 1 Year | Yes
1 |  | Communication | Communicate information on event using Event Summary |  | 2016-11-09 | 2016-12-01
| Lori |  | Action Item to Accomplish Task | Communicate? | Start Date | End Date
| Lori |  | Complete initial Implementation & Communication Plan |  | 2016-11-09 | 2016-11-18
| Lori |  | Post on shared drive for multiple users | Yes | 2016-11-18 | 2016-11-18
| Lori |  | Post I & C Plan to DNR website | Yes | 2016-11-09 | 2016-12-01
| Lori |  | share during Client Contact Meeting | Yes | 2016-11-17 | 2016-11-17
2 |  | Data Sharing - calc request | Implement Data Sharing | Yes |  | 7 days
| Chris |  | Action Item to Accomplish Task | Communicate? | Start Date | End Date
| Chris |  | develop method for request (add to 30-day email/letter) |  | 2016-11-28 | 2016-11-30
3 |  | Data Sharing - calc request | Update SOP & Communicate to staff |  | 2016-11-28 | 2016-11-30
| Chris |  | Action Item to Accomplish Task | Communicate? | Start Date | End Date
| Chris |  | Review updates and share with staff | Yes | 2016-11-28 | 2016-11-30
4 |  | Internal Info. Requests "live" document | Implement Internal Info. Request | Yes |  | 30 days
| Jessica |  | Action Item to Accomplish Task | Communicate? | Start Date | End Date
5 |  | Internal Info. Requests "live" document | Create file in Air Quality shared directory |  | 2016-11-07 | 2016-11-18
| Lori |  | Action Item to Accomplish Task | Communicate? | Start Date | End Date
| Lori |  | created folder |  | 2016-11-07 | 2016-11-07
| Lori |  | moved facility data from Compliance |  | 2016-11-07 | 2016-11-07
6 |  | Internal Info. Requests "live" document | Update SOP |  | 2016-10-27 | 2016-11-15
| Jessica |  | Action Item to Accomplish Task | Communicate? | Start Date | End Date
| Jessica |  | develop naming scheme for subfolders |  | 2016-10-27 | 2016-11-15
| Jessica |  | meet with TV and C&E staff |  | 2016-11-15 | 2016-11-15
| Jessica |  | Update Request Form |  | 2016-11-15 | 2016-11-15
7 |  | Internal Info. Requests "live" document | Training - Title V & Air Quality Staff |  | 2016-11-17 | 2016-11-18
| Jessica |  | Action Item to Accomplish Task | Communicate? | Start Date | End Date
| Jessica |  | Share naming scheme at TV section mtg |  | 2016-11-17 | 2016-11-17
| Jessica |  | Share naming scheme with other sections |  | 2016-11-17 | 2016-11-18
8 |  | Performance measures | Implement performance measures | Yes |  | 30 days
| Lori |  | Action Item to Accomplish Task | Communicate? | Start Date | End Date
9 |  | Performance measures | Create & Define performance measures |  | 2016-10-21 | 2016-12-01
| Weston |  | Action Item to Accomplish Task | Communicate? | Start Date | End Date
| Weston |  | discuss type of data to track with section |  | 2016-10-21 | 2016-11-03
| Weston |  | change database |  | 2016-11-01 | 2016-11-03
10 |  | Performance measures | Update SOP & docs |  | 2016-11-28 | 2016-12-01
| Chris |  | Action Item to Accomplish Task | Communicate? | Start Date | End Date
| Chris |  | Review updates and share with staff |  | 2016-11-28 | 2016-12-01
11 |  | Performance measures | Training Staff |  | 2016-11-03 | 2016-11-04
| Weston |  | Action Item to Accomplish Task | Communicate? | Start Date | End Date
| Weston |  | train TV staff |  | 2016-11-03 | 2016-11-03
12 |  | Performance measures | Customer Satisfaction Survey |  | 2016-11-03 | 2016-11-04
| Lori |  | Action Item to Accomplish Task | Communicate? | Start Date | End Date
| Julie |  | Develop email template |  | 2016-11-03 | 2016-11-04
| Julie |  | Ddevelop response tracking form |  | 2016-11-03 | 2016-11-04
13 |  | Performance measures | Share & Communicate data (in Air Quality & to customers)
| Lori |  | Action Item to Accomplish Task | Communicate? | Start Date | End Date
| Lori |  | share during Client Contact Meeting | Yes | 2016-11-17 | 2016-11-17
| Lori |  | post to website | Yes | 2016-11-30 | 2016-12-01
14 |  | Pre-meeting | Implement Pre-meeting | Yes |  | 9 months
| Lori |  | Action Item to Accomplish Task | Communicate? | Start Date | End Date
| Lori |  | Discuss with Catharine 11/14/16 |  | 2016-11-14 | 2016-11-14
| Lori |  | set date |  | 2016-11-14 | 2016-11-15
| Lori |  | invite stakeholders |  | 2016-11-17 | 2016-11-30
15 |  | Pre-meeting | Create SOP & Documents that drive the Pre-meeting
| Weston |  | Action Item to Accomplish Task | Communicate? | Start Date | End Date
16 |  | Pre-meeting | Communication to stakeholders
| Lori |  | Action Item to Accomplish Task | Communicate? | Start Date | End Date
|  |  | Initial stake holder meeting for input (concurrent with forms meeting) |  |  | 90 days
| Lori |  | check on room availability 1/17 -1/20 |  | 2016-11-14
17 |  | Pre-meeting | Training of Pre-meeting
| Lori |  | Action Item to Accomplish Task | Communicate? | Start Date | End Date
18 |  | Pre-technical meeting | Implement Pre-technical meeting | Yes |  | 9 months
| Lori |  | Action Item to Accomplish Task | Communicate? | Start Date | End Date
| Lori |  | Discuss with Catharine 11/14/16 |  | 2016-11-14 | 2016-11-14
| Lori |  | set date |  | 2016-11-14 | 2016-11-17
| Lori |  | invite stakeholders |  | 2016-11-17 | 2016-12-01
19 |  | Pre-technical meeting | Create Documents that drive the Pre-meeting
| Weston |  | Action Item to Accomplish Task | Communicate? | Start Date | End Date
20 |  | Pre-technical meeting | Create SOP that drive the Pre-meeting
| Chris |  | Action Item to Accomplish Task | Communicate? | Start Date | End Date
21 |  | Pre-technical meeting | Communication to stakeholders
| Lori |  | Action Item to Accomplish Task | Communicate? | Start Date | End Date
|  |  | Initial stake holder meeting for input (concurrent with forms meeting) |  |  | 90 days
22 |  | Pre-technical meeting | Training of Pre-meeting
| Weston |  | Action Item to Accomplish Task | Communicate? | Start Date | End Date
23 |  | Forms Evaluation | Implement Form Changes | Yes |  | 9 months
| Lori |  | Action Item to Accomplish Task | Communicate? | Start Date | End Date
| Lori |  | Discuss with Catharine 11/14/16 |  | 2016-11-14 | 2016-11-14
| Lori |  | Set date |  | 2016-11-14 | 2016-11-14
| Lori |  | Invite stakeholders |  | 2016-11-17 | 112/1/16
24 |  | Forms Evaluation | Stakeholder meeting |  |  | 90 days
| Lori |  | Action Item to Accomplish Task | Communicate? | Start Date | End Date
25 |  | Forms Evaluation | Recommendations of changes
| Lori |  | Action Item to Accomplish Task | Communicate? | Start Date | End Date
26 |  | Forms Evaluation | Quick/Simple changes @ 6 months
|  |  | Action Item to Accomplish Task | Communicate? | Start Date | End Date
27 |  | Forms Evaluation | Potential larger or e-application changes @ 12 months
|  |  | Action Item to Accomplish Task | Communicate? | Start Date | End Date
28 |  | Forms Evaluation | Stakeholder meeting for approval
| Lori |  | Action Item to Accomplish Task | Communicate? | Start Date | End Date
29 |  | Forms Evaluation | Federal & legal approvals
| Lori |  | Action Item to Accomplish Task | Communicate? | Start Date | End Date
| Anne |  | Legal review
| Lori |  | EPA review
30 |  | Forms Evaluation | Update SOP & Docs
| Chris |  | Action Item to Accomplish Task | Communicate? | Start Date | End Date
31 |  | Forms Evaluation | Training Staff & Customers
| Chris |  | Action Item to Accomplish Task | Communicate? | Start Date | End Date
32 |  |  |  | Yes
| Lori |  | Action Item to Accomplish Task | Communicate? | Start Date | End Date
Additional Items/Parking Lot
| Chris |  | develop FAQ for modifications
| Chris |  | training on modifications
| Anne P |  | Are signatures required for supplemental information?
| Lori |  | Review expectations of the internal senior review
LEGEND
GR | Timeline for completion
G | Going well
Y | Concern or behind schedule
R | Critical issue - can't move forward
B | Completion
C | Clear indicates - No action needed at this time
Note on B2: Person responsible for ensuring action items are completed and the task is implemented. If there are multiple people assisting with completing the task, a lead person must be identified. The lead person is responsible for entering action items and entering updates on implementation.
Note on D2: What needs done in order for the new process to occur.
Note on E2: Does the task and/or action item(s) need communicated? If "yes" - select "yes" for that item. The plan is then to be completed. May include need to be shared through training.
Note on F2: Date the Task item will start being worked on. Date should be determined no later than at 30 day.
Note on G2: Date the task will be put into effect. Date should be determined no later than at 30 day.
Note on T2: Update on implementation of task. Entered by "lead person responsible" prior to the follow-up meeting.
Note on U2: Update on implementation of task. Entered by "lead person responsible" prior to the follow-up meeting.
Note on V2: Update on implementation of task. Entered by "lead person responsible" prior to the follow-up meeting.
Note on W2: Update on implementation of task. Entered by "lead person responsible" prior to the follow-up meeting.
Note on X2: Update on implementation of task. Entered by "lead person responsible" prior to the follow-up meeting.
Note on D3: To be completed within 30 days of the event.
Note on B4: Can enter name(s) of person responsible for each action item. This is optional
Note on D4: The steps that need to be completed in order to implement the overall task item. The "lead person responsible" is responsible for entering the action items based on input from others working on the actions steps.
Note on E4: Does the task and/or action item(s) need communicated? If "yes" - select "yes" for that item. The plan is then to be completed. May include need to be shared through training.
Note on F4: Date the action item will start being worked on.
Note on G4: Date action item will be completed.
Note on H4: Implementation Status. Entered by facilitator or sub-team leader. Grey = Timeline for completion Green = Going well Yellow = Concern or behind schedule Red = Critical issue, can't move forward Blue = Completed Clear = No Action needed
Note on T4: Teams can enter their updates on each action item if they chose. This is optional
Note on U4: Teams can enter their updates on each action item if they chose. This is optional
Note on V4: Teams can enter their updates on each action item if they chose. This is optional
Note on W4: Teams can enter their updates on each action item if they chose. This is optional
Note on X4: Teams can enter their updates on each action item if they chose. This is optional
Note on B11: Can enter name(s) of person responsible for each action item. This is optional
Note on D11: The steps that need to be completed in order to implement the overall task item. The "lead person responsible" is responsible for entering the action items based on input from others working on the actions steps.
Note on F11: Date the action item will start being worked on.
Note on G11: Date action item will be completed.
Note on H11: Implementation Status. Entered by facilitator or sub-team leader. Grey = Timeline for completion Green = Going well Yellow = Concern or behind schedule Red = Critical issue, can't move forward Blue = Completed Clear = No Action needed
Note on T11: Teams can enter their updates on each action item if they chose. This is optional
Note on U11: Teams can enter their updates on each action item if they chose. This is optional
Note on V11: Teams can enter their updates on each action item if they chose. This is optional
Note on W11: Teams can enter their updates on each action item if they chose. This is optional
Note on X11: Teams can enter their updates on each action item if they chose. This is optional
Note on B14: Can enter name(s) of person responsible for each action item. This is optional
Note on D14: The steps that need to be completed in order to implement the overall task item. The "lead person responsible" is responsible for entering the action items based on input from others working on the actions steps.
Note on F14: Date the action item will start being worked on.
Note on G14: Date action item will be completed.
Note on H14: Implementation Status. Entered by facilitator or sub-team leader. Grey = Timeline for completion Green = Going well Yellow = Concern or behind schedule Red = Critical issue, can't move forward Blue = Completed Clear = No Action needed
Note on T14: Teams can enter their updates on each action item if they chose. This is optional
Note on U14: Teams can enter their updates on each action item if they chose. This is optional
Note on V14: Teams can enter their updates on each action item if they chose. This is optional
Note on W14: Teams can enter their updates on each action item if they chose. This is optional
Note on X14: Teams can enter their updates on each action item if they chose. This is optional
Note on B18: Can enter name(s) of person responsible for each action item. This is optional
Note on D18: The steps that need to be completed in order to implement the overall task item. The "lead person responsible" is responsible for entering the action items based on input from others working on the actions steps.
Note on F18: Date the action item will start being worked on.
Note on G18: Date action item will be completed.
Note on H18: Implementation Status. Entered by facilitator or sub-team leader. Grey = Timeline for completion Green = Going well Yellow = Concern or behind schedule Red = Critical issue, can't move forward Blue = Completed Clear = No Action needed
Note on T18: Teams can enter their updates on each action item if they chose. This is optional
Note on U18: Teams can enter their updates on each action item if they chose. This is optional
Note on V18: Teams can enter their updates on each action item if they chose. This is optional
Note on W18: Teams can enter their updates on each action item if they chose. This is optional
Note on X18: Teams can enter their updates on each action item if they chose. This is optional
Note on B20: Can enter name(s) of person responsible for each action item. This is optional
Note on D20: The steps that need to be completed in order to implement the overall task item. The "lead person responsible" is responsible for entering the action items based on input from others working on the actions steps.
Note on F20: Date the action item will start being worked on.
Note on G20: Date action item will be completed.
Note on H20: Implementation Status. Entered by facilitator or sub-team leader. Grey = Timeline for completion Green = Going well Yellow = Concern or behind schedule Red = Critical issue, can't move forward Blue = Completed Clear = No Action needed
Note on T20: Teams can enter their updates on each action item if they chose. This is optional
Note on U20: Teams can enter their updates on each action item if they chose. This is optional
Note on V20: Teams can enter their updates on each action item if they chose. This is optional
Note on W20: Teams can enter their updates on each action item if they chose. This is optional
Note on X20: Teams can enter their updates on each action item if they chose. This is optional
Note on B24: Can enter name(s) of person responsible for each action item. This is optional
Note on D24: The steps that need to be completed in order to implement the overall task item. The "lead person responsible" is responsible for entering the action items based on input from others working on the actions steps.
Note on F24: Date the action item will start being worked on.
Note on G24: Date action item will be completed.
Note on H24: Implementation Status. Entered by facilitator or sub-team leader. Grey = Timeline for completion Green = Going well Yellow = Concern or behind schedule Red = Critical issue, can't move forward Blue = Completed Clear = No Action needed
Note on T24: Teams can enter their updates on each action item if they chose. This is optional
Note on U24: Teams can enter their updates on each action item if they chose. This is optional
Note on V24: Teams can enter their updates on each action item if they chose. This is optional
Note on W24: Teams can enter their updates on each action item if they chose. This is optional
Note on X24: Teams can enter their updates on each action item if they chose. This is optional
Note on B29: Can enter name(s) of person responsible for each action item. This is optional
Note on D29: The steps that need to be completed in order to implement the overall task item. The "lead person responsible" is responsible for entering the action items based on input from others working on the actions steps.
Note on F29: Date the action item will start being worked on.
Note on G29: Date action item will be completed.
Note on H29: Implementation Status. Entered by facilitator or sub-team leader. Grey = Timeline for completion Green = Going well Yellow = Concern or behind schedule Red = Critical issue, can't move forward Blue = Completed Clear = No Action needed
Note on T29: Teams can enter their updates on each action item if they chose. This is optional
Note on U29: Teams can enter their updates on each action item if they chose. This is optional
Note on V29: Teams can enter their updates on each action item if they chose. This is optional
Note on W29: Teams can enter their updates on each action item if they chose. This is optional
Note on X29: Teams can enter their updates on each action item if they chose. This is optional
Note on B34: Can enter name(s) of person responsible for each action item. This is optional
Note on D34: The steps that need to be completed in order to implement the overall task item. The "lead person responsible" is responsible for entering the action items based on input from others working on the actions steps.
Note on F34: Date the action item will start being worked on.
Note on G34: Date action item will be completed.
Note on H34: Implementation Status. Entered by facilitator or sub-team leader. Grey = Timeline for completion Green = Going well Yellow = Concern or behind schedule Red = Critical issue, can't move forward Blue = Completed Clear = No Action needed
Note on T34: Teams can enter their updates on each action item if they chose. This is optional
Note on U34: Teams can enter their updates on each action item if they chose. This is optional
Note on V34: Teams can enter their updates on each action item if they chose. This is optional
Note on W34: Teams can enter their updates on each action item if they chose. This is optional
Note on X34: Teams can enter their updates on each action item if they chose. This is optional
Note on B36: Can enter name(s) of person responsible for each action item. This is optional
Note on D36: The steps that need to be completed in order to implement the overall task item. The "lead person responsible" is responsible for entering the action items based on input from others working on the actions steps.
Note on F36: Date the action item will start being worked on.
Note on G36: Date action item will be completed.
Note on H36: Implementation Status. Entered by facilitator or sub-team leader. Grey = Timeline for completion Green = Going well Yellow = Concern or behind schedule Red = Critical issue, can't move forward Blue = Completed Clear = No Action needed
Note on T36: Teams can enter their updates on each action item if they chose. This is optional
Note on U36: Teams can enter their updates on each action item if they chose. This is optional
Note on V36: Teams can enter their updates on each action item if they chose. This is optional
Note on W36: Teams can enter their updates on each action item if they chose. This is optional
Note on X36: Teams can enter their updates on each action item if they chose. This is optional
Note on B40: Can enter name(s) of person responsible for each action item. This is optional
Note on D40: The steps that need to be completed in order to implement the overall task item. The "lead person responsible" is responsible for entering the action items based on input from others working on the actions steps.
Note on F40: Date the action item will start being worked on.
Note on G40: Date action item will be completed.
Note on H40: Implementation Status. Entered by facilitator or sub-team leader. Grey = Timeline for completion Green = Going well Yellow = Concern or behind schedule Red = Critical issue, can't move forward Blue = Completed Clear = No Action needed
Note on T40: Teams can enter their updates on each action item if they chose. This is optional
Note on U40: Teams can enter their updates on each action item if they chose. This is optional
Note on V40: Teams can enter their updates on each action item if they chose. This is optional
Note on W40: Teams can enter their updates on each action item if they chose. This is optional
Note on X40: Teams can enter their updates on each action item if they chose. This is optional
Note on B43: Can enter name(s) of person responsible for each action item. This is optional
Note on D43: The steps that need to be completed in order to implement the overall task item. The "lead person responsible" is responsible for entering the action items based on input from others working on the actions steps.
Note on F43: Date the action item will start being worked on.
Note on G43: Date action item will be completed.
Note on H43: Implementation Status. Entered by facilitator or sub-team leader. Grey = Timeline for completion Green = Going well Yellow = Concern or behind schedule Red = Critical issue, can't move forward Blue = Completed Clear = No Action needed
Note on T43: Teams can enter their updates on each action item if they chose. This is optional
Note on U43: Teams can enter their updates on each action item if they chose. This is optional
Note on V43: Teams can enter their updates on each action item if they chose. This is optional
Note on W43: Teams can enter their updates on each action item if they chose. This is optional
Note on X43: Teams can enter their updates on each action item if they chose. This is optional
Note on B46: Can enter name(s) of person responsible for each action item. This is optional
Note on D46: The steps that need to be completed in order to implement the overall task item. The "lead person responsible" is responsible for entering the action items based on input from others working on the actions steps.
Note on F46: Date the action item will start being worked on.
Note on G46: Date action item will be completed.
Note on H46: Implementation Status. Entered by facilitator or sub-team leader. Grey = Timeline for completion Green = Going well Yellow = Concern or behind schedule Red = Critical issue, can't move forward Blue = Completed Clear = No Action needed
Note on T46: Teams can enter their updates on each action item if they chose. This is optional
Note on U46: Teams can enter their updates on each action item if they chose. This is optional
Note on V46: Teams can enter their updates on each action item if they chose. This is optional
Note on W46: Teams can enter their updates on each action item if they chose. This is optional
Note on X46: Teams can enter their updates on each action item if they chose. This is optional
Note on B50: Can enter name(s) of person responsible for each action item. This is optional
Note on D50: The steps that need to be completed in order to implement the overall task item. The "lead person responsible" is responsible for entering the action items based on input from others working on the actions steps.
Note on F50: Date the action item will start being worked on.
Note on G50: Date action item will be completed.
Note on H50: Implementation Status. Entered by facilitator or sub-team leader. Grey = Timeline for completion Green = Going well Yellow = Concern or behind schedule Red = Critical issue, can't move forward Blue = Completed Clear = No Action needed
Note on T50: Teams can enter their updates on each action item if they chose. This is optional
Note on U50: Teams can enter their updates on each action item if they chose. This is optional
Note on V50: Teams can enter their updates on each action item if they chose. This is optional
Note on W50: Teams can enter their updates on each action item if they chose. This is optional
Note on X50: Teams can enter their updates on each action item if they chose. This is optional
Note on B55: Can enter name(s) of person responsible for each action item. This is optional
Note on D55: The steps that need to be completed in order to implement the overall task item. The "lead person responsible" is responsible for entering the action items based on input from others working on the actions steps.
Note on F55: Date the action item will start being worked on.
Note on G55: Date action item will be completed.
Note on H55: Implementation Status. Entered by facilitator or sub-team leader. Grey = Timeline for completion Green = Going well Yellow = Concern or behind schedule Red = Critical issue, can't move forward Blue = Completed Clear = No Action needed
Note on T55: Teams can enter their updates on each action item if they chose. This is optional
Note on U55: Teams can enter their updates on each action item if they chose. This is optional
Note on V55: Teams can enter their updates on each action item if they chose. This is optional
Note on W55: Teams can enter their updates on each action item if they chose. This is optional
Note on X55: Teams can enter their updates on each action item if they chose. This is optional
Note on B60: Can enter name(s) of person responsible for each action item. This is optional
Note on D60: The steps that need to be completed in order to implement the overall task item. The "lead person responsible" is responsible for entering the action items based on input from others working on the actions steps.
Note on F60: Date the action item will start being worked on.
Note on G60: Date action item will be completed.
Note on H60: Implementation Status. Entered by facilitator or sub-team leader. Grey = Timeline for completion Green = Going well Yellow = Concern or behind schedule Red = Critical issue, can't move forward Blue = Completed Clear = No Action needed
Note on T60: Teams can enter their updates on each action item if they chose. This is optional
Note on U60: Teams can enter their updates on each action item if they chose. This is optional
Note on V60: Teams can enter their updates on each action item if they chose. This is optional
Note on W60: Teams can enter their updates on each action item if they chose. This is optional
Note on X60: Teams can enter their updates on each action item if they chose. This is optional
Note on B65: Can enter name(s) of person responsible for each action item. This is optional
Note on D65: The steps that need to be completed in order to implement the overall task item. The "lead person responsible" is responsible for entering the action items based on input from others working on the actions steps.
Note on F65: Date the action item will start being worked on.
Note on G65: Date action item will be completed.
Note on H65: Implementation Status. Entered by facilitator or sub-team leader. Grey = Timeline for completion Green = Going well Yellow = Concern or behind schedule Red = Critical issue, can't move forward Blue = Completed Clear = No Action needed
Note on T65: Teams can enter their updates on each action item if they chose. This is optional
Note on U65: Teams can enter their updates on each action item if they chose. This is optional
Note on V65: Teams can enter their updates on each action item if they chose. This is optional
Note on W65: Teams can enter their updates on each action item if they chose. This is optional
Note on X65: Teams can enter their updates on each action item if they chose. This is optional
Note on B72: Can enter name(s) of person responsible for each action item. This is optional
Note on D72: The steps that need to be completed in order to implement the overall task item. The "lead person responsible" is responsible for entering the action items based on input from others working on the actions steps.
Note on F72: Date the action item will start being worked on.
Note on G72: Date action item will be completed.
Note on H72: Implementation Status. Entered by facilitator or sub-team leader. Grey = Timeline for completion Green = Going well Yellow = Concern or behind schedule Red = Critical issue, can't move forward Blue = Completed Clear = No Action needed
Note on T72: Teams can enter their updates on each action item if they chose. This is optional
Note on U72: Teams can enter their updates on each action item if they chose. This is optional
Note on V72: Teams can enter their updates on each action item if they chose. This is optional
Note on W72: Teams can enter their updates on each action item if they chose. This is optional
Note on X72: Teams can enter their updates on each action item if they chose. This is optional
Note on B77: Can enter name(s) of person responsible for each action item. This is optional
Note on D77: The steps that need to be completed in order to implement the overall task item. The "lead person responsible" is responsible for entering the action items based on input from others working on the actions steps.
Note on F77: Date the action item will start being worked on.
Note on G77: Date action item will be completed.
Note on H77: Implementation Status. Entered by facilitator or sub-team leader. Grey = Timeline for completion Green = Going well Yellow = Concern or behind schedule Red = Critical issue, can't move forward Blue = Completed Clear = No Action needed
Note on T77: Teams can enter their updates on each action item if they chose. This is optional
Note on U77: Teams can enter their updates on each action item if they chose. This is optional
Note on V77: Teams can enter their updates on each action item if they chose. This is optional
Note on W77: Teams can enter their updates on each action item if they chose. This is optional
Note on X77: Teams can enter their updates on each action item if they chose. This is optional
Note on B83: Can enter name(s) of person responsible for each action item. This is optional
Note on D83: The steps that need to be completed in order to implement the overall task item. The "lead person responsible" is responsible for entering the action items based on input from others working on the actions steps.
Note on F83: Date the action item will start being worked on.
Note on G83: Date action item will be completed.
Note on H83: Implementation Status. Entered by facilitator or sub-team leader. Grey = Timeline for completion Green = Going well Yellow = Concern or behind schedule Red = Critical issue, can't move forward Blue = Completed Clear = No Action needed
Note on T83: Teams can enter their updates on each action item if they chose. This is optional
Note on U83: Teams can enter their updates on each action item if they chose. This is optional
Note on V83: Teams can enter their updates on each action item if they chose. This is optional
Note on W83: Teams can enter their updates on each action item if they chose. This is optional
Note on X83: Teams can enter their updates on each action item if they chose. This is optional
Note on B88: Can enter name(s) of person responsible for each action item. This is optional
Note on D88: The steps that need to be completed in order to implement the overall task item. The "lead person responsible" is responsible for entering the action items based on input from others working on the actions steps.
Note on F88: Date the action item will start being worked on.
Note on G88: Date action item will be completed.
Note on H88: Implementation Status. Entered by facilitator or sub-team leader. Grey = Timeline for completion Green = Going well Yellow = Concern or behind schedule Red = Critical issue, can't move forward Blue = Completed Clear = No Action needed
Note on T88: Teams can enter their updates on each action item if they chose. This is optional
Note on U88: Teams can enter their updates on each action item if they chose. This is optional
Note on V88: Teams can enter their updates on each action item if they chose. This is optional
Note on W88: Teams can enter their updates on each action item if they chose. This is optional
Note on X88: Teams can enter their updates on each action item if they chose. This is optional
Note on B93: Can enter name(s) of person responsible for each action item. This is optional
Note on D93: The steps that need to be completed in order to implement the overall task item. The "lead person responsible" is responsible for entering the action items based on input from others working on the actions steps.
Note on F93: Date the action item will start being worked on.
Note on G93: Date action item will be completed.
Note on H93: Implementation Status. Entered by facilitator or sub-team leader. Grey = Timeline for completion Green = Going well Yellow = Concern or behind schedule Red = Critical issue, can't move forward Blue = Completed Clear = No Action needed
Note on T93: Teams can enter their updates on each action item if they chose. This is optional
Note on U93: Teams can enter their updates on each action item if they chose. This is optional
Note on V93: Teams can enter their updates on each action item if they chose. This is optional
Note on W93: Teams can enter their updates on each action item if they chose. This is optional
Note on X93: Teams can enter their updates on each action item if they chose. This is optional
Note on B98: Can enter name(s) of person responsible for each action item. This is optional
Note on D98: The steps that need to be completed in order to implement the overall task item. The "lead person responsible" is responsible for entering the action items based on input from others working on the actions steps.
Note on F98: Date the action item will start being worked on.
Note on G98: Date action item will be completed.
Note on H98: Implementation Status. Entered by facilitator or sub-team leader. Grey = Timeline for completion Green = Going well Yellow = Concern or behind schedule Red = Critical issue, can't move forward Blue = Completed Clear = No Action needed
Note on T98: Teams can enter their updates on each action item if they chose. This is optional
Note on U98: Teams can enter their updates on each action item if they chose. This is optional
Note on V98: Teams can enter their updates on each action item if they chose. This is optional
Note on W98: Teams can enter their updates on each action item if they chose. This is optional
Note on X98: Teams can enter their updates on each action item if they chose. This is optional
Note on B103: Can enter name(s) of person responsible for each action item. This is optional
Note on D103: The steps that need to be completed in order to implement the overall task item. The "lead person responsible" is responsible for entering the action items based on input from others working on the actions steps.
Note on F103: Date the action item will start being worked on.
Note on G103: Date action item will be completed.
Note on H103: Implementation Status. Entered by facilitator or sub-team leader. Grey = Timeline for completion Green = Going well Yellow = Concern or behind schedule Red = Critical issue, can't move forward Blue = Completed Clear = No Action needed
Note on T103: Teams can enter their updates on each action item if they chose. This is optional
Note on U103: Teams can enter their updates on each action item if they chose. This is optional
Note on V103: Teams can enter their updates on each action item if they chose. This is optional
Note on W103: Teams can enter their updates on each action item if they chose. This is optional
Note on X103: Teams can enter their updates on each action item if they chose. This is optional
Note on B108: Can enter name(s) of person responsible for each action item. This is optional
Note on D108: The steps that need to be completed in order to implement the overall task item. The "lead person responsible" is responsible for entering the action items based on input from others working on the actions steps.
Note on F108: Date the action item will start being worked on.
Note on G108: Date action item will be completed.
Note on H108: Implementation Status. Entered by facilitator or sub-team leader. Grey = Timeline for completion Green = Going well Yellow = Concern or behind schedule Red = Critical issue, can't move forward Blue = Completed Clear = No Action needed
Note on T108: Teams can enter their updates on each action item if they chose. This is optional
Note on U108: Teams can enter their updates on each action item if they chose. This is optional
Note on V108: Teams can enter their updates on each action item if they chose. This is optional
Note on W108: Teams can enter their updates on each action item if they chose. This is optional
Note on X108: Teams can enter their updates on each action item if they chose. This is optional
Note on B113: Can enter name(s) of person responsible for each action item. This is optional
Note on D113: The steps that need to be completed in order to implement the overall task item. The "lead person responsible" is responsible for entering the action items based on input from others working on the actions steps.
Note on F113: Date the action item will start being worked on.
Note on G113: Date action item will be completed.
Note on H113: Implementation Status. Entered by facilitator or sub-team leader. Grey = Timeline for completion Green = Going well Yellow = Concern or behind schedule Red = Critical issue, can't move forward Blue = Completed Clear = No Action needed
Note on T113: Teams can enter their updates on each action item if they chose. This is optional
Note on U113: Teams can enter their updates on each action item if they chose. This is optional
Note on V113: Teams can enter their updates on each action item if they chose. This is optional
Note on W113: Teams can enter their updates on each action item if they chose. This is optional
Note on X113: Teams can enter their updates on each action item if they chose. This is optional
Note on B118: Can enter name(s) of person responsible for each action item. This is optional
Note on D118: The steps that need to be completed in order to implement the overall task item. The "lead person responsible" is responsible for entering the action items based on input from others working on the actions steps.
Note on F118: Date the action item will start being worked on.
Note on G118: Date action item will be completed.
Note on H118: Implementation Status. Entered by facilitator or sub-team leader. Grey = Timeline for completion Green = Going well Yellow = Concern or behind schedule Red = Critical issue, can't move forward Blue = Completed Clear = No Action needed
Note on T118: Teams can enter their updates on each action item if they chose. This is optional
Note on U118: Teams can enter their updates on each action item if they chose. This is optional
Note on V118: Teams can enter their updates on each action item if they chose. This is optional
Note on W118: Teams can enter their updates on each action item if they chose. This is optional
Note on X118: Teams can enter their updates on each action item if they chose. This is optional
Note on B122: Can enter name(s) of person responsible for each action item. This is optional
Note on D122: The steps that need to be completed in order to implement the overall task item. The "lead person responsible" is responsible for entering the action items based on input from others working on the actions steps.
Note on F122: Date the action item will start being worked on.
Note on G122: Date action item will be completed.
Note on H122: Implementation Status. Entered by facilitator or sub-team leader. Grey = Timeline for completion Green = Going well Yellow = Concern or behind schedule Red = Critical issue, can't move forward Blue = Completed Clear = No Action needed
Note on T122: Teams can enter their updates on each action item if they chose. This is optional
Note on U122: Teams can enter their updates on each action item if they chose. This is optional
Note on V122: Teams can enter their updates on each action item if they chose. This is optional
Note on W122: Teams can enter their updates on each action item if they chose. This is optional
Note on X122: Teams can enter their updates on each action item if they chose. This is optional
Note on B127: Can enter name(s) of person responsible for each action item. This is optional
Note on D127: The steps that need to be completed in order to implement the overall task item. The "lead person responsible" is responsible for entering the action items based on input from others working on the actions steps.
Note on F127: Date the action item will start being worked on.
Note on G127: Date action item will be completed.
Note on H127: Implementation Status. Entered by facilitator or sub-team leader. Grey = Timeline for completion Green = Going well Yellow = Concern or behind schedule Red = Critical issue, can't move forward Blue = Completed Clear = No Action needed
Note on T127: Teams can enter their updates on each action item if they chose. This is optional
Note on U127: Teams can enter their updates on each action item if they chose. This is optional
Note on V127: Teams can enter their updates on each action item if they chose. This is optional
Note on W127: Teams can enter their updates on each action item if they chose. This is optional
Note on X127: Teams can enter their updates on each action item if they chose. This is optional
Note on B132: Can enter name(s) of person responsible for each action item. This is optional
Note on D132: The steps that need to be completed in order to implement the overall task item. The "lead person responsible" is responsible for entering the action items based on input from others working on the actions steps.
Note on F132: Date the action item will start being worked on.
Note on G132: Date action item will be completed.
Note on H132: Implementation Status. Entered by facilitator or sub-team leader. Grey = Timeline for completion Green = Going well Yellow = Concern or behind schedule Red = Critical issue, can't move forward Blue = Completed Clear = No Action needed
Note on T132: Teams can enter their updates on each action item if they chose. This is optional
Note on U132: Teams can enter their updates on each action item if they chose. This is optional
Note on V132: Teams can enter their updates on each action item if they chose. This is optional
Note on W132: Teams can enter their updates on each action item if they chose. This is optional
Note on X132: Teams can enter their updates on each action item if they chose. This is optional
Note on B137: Can enter name(s) of person responsible for each action item. This is optional
Note on D137: The steps that need to be completed in order to implement the overall task item. The "lead person responsible" is responsible for entering the action items based on input from others working on the actions steps.
Note on F137: Date the action item will start being worked on.
Note on G137: Date action item will be completed.
Note on H137: Implementation Status. Entered by facilitator or sub-team leader. Grey = Timeline for completion Green = Going well Yellow = Concern or behind schedule Red = Critical issue, can't move forward Blue = Completed Clear = No Action needed
Note on T137: Teams can enter their updates on each action item if they chose. This is optional
Note on U137: Teams can enter their updates on each action item if they chose. This is optional
Note on V137: Teams can enter their updates on each action item if they chose. This is optional
Note on W137: Teams can enter their updates on each action item if they chose. This is optional
Note on X137: Teams can enter their updates on each action item if they chose. This is optional
Note on B143: Can enter name(s) of person responsible for each action item. This is optional
Note on D143: The steps that need to be completed in order to implement the overall task item. The "lead person responsible" is responsible for entering the action items based on input from others working on the actions steps.
Note on F143: Date the action item will start being worked on.
Note on G143: Date action item will be completed.
Note on H143: Implementation Status. Entered by facilitator or sub-team leader. Grey = Timeline for completion Green = Going well Yellow = Concern or behind schedule Red = Critical issue, can't move forward Blue = Completed Clear = No Action needed
Note on T143: Teams can enter their updates on each action item if they chose. This is optional
Note on U143: Teams can enter their updates on each action item if they chose. This is optional
Note on V143: Teams can enter their updates on each action item if they chose. This is optional
Note on W143: Teams can enter their updates on each action item if they chose. This is optional
Note on X143: Teams can enter their updates on each action item if they chose. This is optional
Note on B149: Can enter name(s) of person responsible for each action item. This is optional
Note on D149: The steps that need to be completed in order to implement the overall task item. The "lead person responsible" is responsible for entering the action items based on input from others working on the actions steps.
Note on F149: Date the action item will start being worked on.
Note on G149: Date action item will be completed.
Note on H149: Implementation Status. Entered by facilitator or sub-team leader. Grey = Timeline for completion Green = Going well Yellow = Concern or behind schedule Red = Critical issue, can't move forward Blue = Completed Clear = No Action needed
Note on T149: Teams can enter their updates on each action item if they chose. This is optional
Note on U149: Teams can enter their updates on each action item if they chose. This is optional
Note on V149: Teams can enter their updates on each action item if they chose. This is optional
Note on W149: Teams can enter their updates on each action item if they chose. This is optional
Note on X149: Teams can enter their updates on each action item if they chose. This is optional

## Communication Plan
Task/Action Item | Audience | Key Message | Delivery Method | Person Responsible | Person Delivering | Date of Communication
| here you could brainstorm all the audiences that need to be told about the task, action item or outcome of the event | what the audience needs to know, use what, when, where, why and how to help draft. There may be more than one key message. | letter, newsletter, email, in-person, website, press release, social media, etc. | who will develop and ensure communication is delivered | identify who is responsible for communicating the message. There may be more than one person | identify when the communication should occur
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
share during Client Contact Meeting
post to website
#REF!
Review updates and share with staff
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
0
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
Note on A1: There may be extra rows that need deleted when no task/action item is pulled over as items on this sheet appear in chronologically order from the Implementation Plan sheet.

## Performance Measures
Charter Goals | Definition of Goal | Baseline | Goal | 30 day | 60 day | 90 day | 6 month | 1 year

## Instructions for Document
Column | Title of Column | Definition/Description | Tips/Tricks
A | Item # | Number of the Task
B | Who's Responsible | Person responsible for ensuring action items are completed and the task is implemented. If there are multiple people assisting with completing the task, a lead person must be identified. The lead person is responsible for entering action items and entering updates on implementation. | To identify lead person may bold or color that persons name. May create a separate column for "Person Responsible" and one for "Work Group".
C | Task (What needs done) | What needs done in order for the new process to be implemented. Items were identified from the "sweet spot" and/or as team developed new process.
C | Action Item to Accomplish Task | The steps that need to be completed in order to implement the overall task item. The "lead person responsible" is responsible for entering the action items based on input from others working on the actions steps.
D | Communication | Does the task and/or action item(s) need communicated? If "yes" - select "yes" for that task/item and the task and/or action item will automatically move to communication plan. The plan is then to be completed. May include need to be shared through training. | For items identified as needing to be communicated, a communication plan is to be completed. See Communication Plan tab.
E | Start Date | Date start working on the steps that need to occur for implementation to happen. | Team may not know the dates because they need to develop the action steps to know all the work that occurs prior to implementation. Person responsible will need to fill in the dates prior to 30 day follow-up.
F | End Date | Date the Task item will be implemented | Team may not know the dates because they need to develop the action steps to know all the work that occurs prior to implementation. Person responsible will need to fill in the dates prior to 30 day follow-up. (Does not have to align with follow-up dates)
G - R | 12 months | Implementation Status. Entered by facilitator or sub-team leader. Grey = Timeline for completion Green = Going well Yellow = Concern or behind schedule Red = Critical issue, can't move forward Blue = Completed Clear = No Action needed | 1.Facilitator will need to enter the months in the chronological order that implementation will occur based on when the event was held. 2.Facilitator or sub-team leader will complete status of item by color coding each action item and the overall task. Start by filling in with grey shading and then change the grey as items are to be worked on.
S | Update on Implementation 30 Day | Brief summary of implementation or lack of implemenation of the task. Can enter the updateds for each action item or the overall item. | Facilitator or sub-team leader will send an email 7 days prior to the follow-up asking the primary lead person to fill in the udpate and return. Then all updates will be copied and pasted into one document (unless all leads can access the document). The team will then be able to review and discuss the implemenation process.
T | Update on Implementation 60 Day | Brief summary of implementation or lack of implemenation of the task. Can enter the updateds for each action item or the overall item.
U | Update on Implementation 90 Day | Brief summary of implementation or lack of implemenation of the task. Can enter the updateds for each action item or the overall item.
V | Update on Implementation 6 month | Brief summary of implementation or lack of implemenation of the task. Can enter the updateds for each action item or the overall item.
W | Update on Implementation 1 year | Brief summary of implementation or lack of implemenation of the task. Can enter the updateds for each action item or the overall item.
Column/Row | How To | Instructions
Column B | Filter | Highlight only column B; select the filter option on the tool bar; check mark the boxes you want to show when filterd. *Names must be entered beside each action item in order for the action item to appear along side of the overall task.
Column/Row Any | Add/Delete | Left click on the Column Letter/Row Number where you want the new column/row added. Once it is highlighted, right click and select insert